| WORKFORCE RACE EQUALITIES STANDARD – ACTION PLAN 2018/19 (Updated February 2019) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WRES INDICATOR | NATIONAL POSITION (FROM NHS WRES DATA ANALYSIS REPORT FROM 2018 SUBMISSION – dated December 2018) | HOW OUR TRUST COMPARES TO NATIONAL POSITION (AS AT 31 MARCH 2018) | HOW OUR TRUST COMPARES TO NATIONAL POSITION (AS AT 31 MARCH 2017) | ACTION – BY WHOM AND TIMESCALE | PROGRESS AS AT: (RAG RATED) |  |  |  |  |
|  |  |  |  |  | KEY: COMPLETE OR ON TRACK |  |  | PROGRESS MADE | NO PROGRESS |
| - % of BME staff in Bands 8-9, VSM (including executive Board members) compared to % of BME staff in the workforce | Nationally the number of VSMs from BME backgrounds is 7% of all VSMs which remains significantly lower than BME representation in the overall NHS workforce (19%) . | We have 7% BME managers (excluding M&D) compared to 13.3% of workforce. | We have 7.2% BME managers (excluding M&D) compared to 12.7% of workforce. This is an improving position and is slightly better than national average | Keep under review – aim for 12.7% in line with BME workforce. | Sandra Berry– March 2019 |  |  |  |  |
| - Relative likelihood of BME staff being appointed from shortlisting compared to that of white staff | Nationally white applicants are 1.45 times more likely (improved from 1.6 times) to be appointed than BME shortlisted applicants, who continue to remain absent from senior grades within AfC pay bands. | This position has improved significantly compared to the same as last year at 0.89 times more likely for white shortlisted applicants to be appointed. | We were broadly the same as national at 1.76 times more likely. However, the national position has improved to 1.60 times more likely for white shortlisted applicants to be appointed. | Analyse whether this is in particular staff groups, grades, or departments. | Sandra Berry – February 2019 |  |  |  |  |
| - Relative likelihood of BME staff entering the formal disciplinary process, compared to that of white staff entering the formal disciplinary process, as measured by entry into a formal disciplinary investigation | Nationally BME staff are 1.24 times more likely to enter disciplinary process and more likely to be disciplined which is an improvement on last year (1.37) | Our BME staff are 1.14 times more likely to enter disciplinary process which is an improvement on last year’s position and better than the national position. | Our BME staff are 1.79 times more likely to enter disciplinary process which is worse than national position. | Continue to monitor – aim to be equal numbers of BME and white entering process. | Sandra Berry – March 2019. |  |  |  |  |
| - Relative likelihood of BME staff accessing non-mandatory training and CPD compared to white staff | Nationally BME staff are 1.15 times more likely to access non-mandatory training and CPD compared to white staff the position nationally has deteriorated from 1.22 last year. | Our BME staff are 1.09 times more likely to access non-mandatory training and CPD compared to white staff. Trust staff overall access to training is low but BME is higher than white. | Our BME staff are more likely to access training than white staff. | Monitor but unlikely to require additional action at this point. | Jo Chant – March 2019 |  |  |  |  |
| WORKFORCE RACE EQUALITIES STANDARD – ACTION PLAN 2017/18 |  |  |  |  |  |  |  |  |  |
| WRES INDICATOR | NATIONAL POSITION (FROM NHS WRES DATA ANALYSIS REPORT FROM 2018 SUBMISSION – dated December 2018) | HOW OUR TRUST COMPARES TO NATIONAL POSITION (AS AT 31 MARCH 2018) | HOW OUR TRUST COMPARES TO NATIONAL POSITION (AS AT 31 MARCH 2017) | ACTION – BY WHOM AND TIMESCALE | PROGRESS AS AT : RAG RATED |  |  |  |  |
|  |  |  |  |  | KEY: ON TRACK |  | PROGRESS MADE |  | NO PROGRESS |
| - % of staff experiencing harassment, bullying or abuse from patients, relatives or the public in last 12 months | Nationally 29% for BME staff and 28% for white staff which shows no improvement from the previous year. | 28% of our BME staff reported that they had experienced harassment, bullying or abuse from patients, this is an increase on last year by 3% but less that the national 29%. White staff 29% reported compared to 32% in previous year but is 1% above the national %. | 25% of our BME staff and 32% of white staff reported that they had experienced harassment, bullying or abuse from patients in 2017 survey. | Continue with full SOS survey for 2019. | Sandra Berry – September 2019 commissioned full survey |  |  |  |  |
|  |  |  |  | Drill this data down to identify problem departments or staff groups. | Sandra Berry– February 2019 once Staff Survey results are available |  |  |  |  |
|  |  |  |  | Set up Staff Engagement Forum with a view to BME network longer term | David Southall – September 2019- Social network forum to be established |  |  |  |  |
| - % of staff experiencing harassment bullying or abuse from staff in last 12 months | Nationally BME staff are more likely to experience discrimination at work from colleagues and managers compared to white staff at 28% and 23% respectively. | Our BME staff reporting harassment, bullying or abuse from staff has improved from 32% in 2017 to 28% in 2018, which is the same as the national position. For White staff has improved from 31% to 28% and but is still worse than the national position by 5%. | Our BME has improved from 56% in 2015 to 32% in 2016 and has remained at 32% for 2017 White has deteriorated from 28% to 31%.Both are significantly higher than national position. | Full SOS survey for 2018 with data drilled down to identify problem departments Sandra Berry– February 2018 once Staff Survey results are available |  |  |  |  |  |
| - % believing that trust provides equal opportunities for career progression or promotion | Nationally 72% for BME and 87% for White staff | Our response has detoriated from 74% in 2017 to 70% in 2018 for BME staff and slightly improved for white staff from 84% to 84.5% | Our response has improved from 69%in 2016 for BME to 74% in 2017 due to full staff survey. For white staff position has improved slightly from 82% in 2016 to 84% in 2017 | BME network group needs to be established to understand why staff feel this way, and what support we need to give. E&D Committee to take a lead. |  | David Southall – March 2019 |  |  |  |

| WORKFORCE RACE EQUALITIES STANDARD – ACTION PLAN 2017/18 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WRES INDICATOR | NATIONAL POSITION (FROM NHS WRES DATA ANALYSIS REPORT FROM 2018 SUBMISSION – dated December 2018) | HOW OUR TRUST COMPARES TO NATIONAL POSITION (AS AT 31 MARCH 2018) | HOW OUR TRUST COMPARES TO NATIONAL POSITION (AS AT 31 MARCH 2017) | ACTION – BY WHOM AND TIMESCALE | PROGRESS AS AT : RAG RATED |  |  |
|  |  |  |  |  | KEY: COMPLETE OR ON TRACK | PROGRESS MADE | NO PROGRESS |
| - In last 12 months % personally experienced discrimination at work from manager, team leader or other colleagues | Nationally 15% for BME and 7% white | Our BME staff response has reduced from 17% in 2017 to 16% in 2018. survey. However this is still slightly worse than national position. For white staff there is little change with 6% in 2017 and 5.98% in 2018 which is better than national position. | Our BME staff response has reduced from 24% in 2016 to 17% in 2017. However this is still worse than national position. For white staff there is little change with 5% in 2015 and 6% in 2016 which is the same as national position. | Continue to promote FTSU Champions and FTSU Guardian – Bryan McGinity –March 2019 |  |  |  |
| - Boards are expected to be broadly representative of the population they serve | Nationally there has been a steady increase in the number of Trusts with at least one BME Board member. 29 Trusts have 3 or more BME members of the board; an increase of 13 trusts since 2017 . | We are 10% against Worcs BME population of 7.6% | We are 0% against Worcs BME population of 7.6% | No action required currently |  |  |  |